## INSERT TITLE
PROJECT NAME: | [5 empty] | RISK ASSESSMENT NUMBER :
PREPARED BY: | [5 empty] | DATE OF CREATION:
APROVED BY: | [5 empty] | REVIEW DATE:
RISK ASSESSMENT: WELDING WORKS ON THE MAIN DECK LEVEL 2 (CONFINED SPACE). TOOLS: TIG WELDER, GRINDER. HAZARDS: TOXIC FUMES, FIRE RISK, HIGH NOISE. CREW: 2 WELDERS, 1 FIRE WATCH. WEATHER: HEAVY RAIN.
NR | HAZARD/ASPECT | INCIDENT(consequence/impact) | CONSEQUENCE | PROBABILITY | RISK | MEASURES CONTROL | CONSEQUENCE | PROBABILITY | RISK | ACTIONS
1 | 1. PREPARATION AND PERMIT TO WORK (PTW) / TOOLBOX TALK (TBT) Confined Space: Oxygen deficiency, accumulation of toxic gases | Asphyxiation or acute poisoning of personnel | 5 | 4 | 20 | - Elimination: Verify atmosphere with gas detector before entry and periodically during work. - Engineering: Ensure forced ventilation is set up and operational. - Admin: Obtain and display valid Confined Space Entry Permit and hot work permit. Daily TBT specific to confined space and welding operations. - Admin: Assign a dedicated, competent confined space attendant/fire watch with radio. - PPE: SCBA available for rescue, use of 4-gas monitor as personal monitor. | 5 | 2 | 10
2 | 1. PREPARATION AND PERMIT TO WORK (PTW) / TOOLBOX TALK (TBT) Incorrect Permitting or Communication failure | Unauthorized personnel exposure to hazard, uncoordinated emergency response | 4 | 4 | 16 | - Admin: Cross-check permits for all task steps (confined space, hot work). Daily TBT to confirm roles and emergency contacts. - Engineering: Radio check for all personnel, signage at the worksite entrance. - Admin: Simultaneous Operations (SIMOPS) review before work. | 4 | 2 | 8
3 | 2. MOBILIZATION / TRANSPORT OF TIG WELDER AND GRINDER TO DECK LEVEL 2 Manual Handling: Lifting heavy equipment (TIG welder >25kg), awkward posture/stairs | Back strain, crush injury, slip/trip/fall | 3 | 4 | 12 | - Engineering: Use mechanical aids (trolley, lift) wherever possible. - Admin: Two-person lift for heavy objects, pre-plan route considering weather/footing. - PPE: Safety footwear with anti-slip soles, gloves. | 3 | 2 | 6
4 | 2. MOBILIZATION / TRANSPORT OF TIG WELDER AND GRINDER TO DECK LEVEL 2 Slips/Trips/Falls due to Heavy Rain and Wet Surfaces | Sprains, fractures, possible head injury | 4 | 3 | 12 | - Engineering: Place anti-slip mats at entry/exit points. - Elimination: Delay mobilization during extreme rain if risk is unmanageable. - Admin: Brief crew on slip/trip hazards during TBT. - PPE: Use non-slip boots. | 4 | 1 | 4
5 | 3A. WELDING SETUP AND EQUIPMENT CHECK Electrical Shock (live cables in wet conditions) | Electrocution, burns | 5 | 3 | 15 | - Elimination: Inspect all cables and connectors for damage before use. - Engineering: Use only equipment with IP-rated (waterproof) protection. - Admin: Ensure socket power is off during connection, use RCD (Residual Current Device) protection. - PPE: Electrical grade gloves, dry welding boots. - Admin: Remove standing water before connecting equipment. | 5 | 1 | 5
6 | 3B. ENTRY AND VENTILATION START-UP Inadequate Ventilation | Build-up of welding fumes, oxygen deficiency causing loss of consciousness | 5 | 4 | 20 | - Engineering: Set up forced ventilation before work commences and regularly monitor airflow. - Admin: Monitor atmosphere with multi-gas meter (O2, CO, CO2, LEL) continuously. - Admin: Stop work immediately if alarms trigger. | 5 | 2 | 10
7 | 3C. EXECUTION OF WELDING (TIG WELDING/GRINDING IN CONFINED SPACE) Toxic Fumes (welding/gas/ozone, especially in confined space) | Respiratory distress, long-term lung damage, acute poisoning | 5 | 4 | 20 | - Engineering: Forced ventilation to maintain fresh air supply. - Admin: Confirm extraction points and airflow direction. - Substitution: Use low-fume consumables if possible. - PPE: Use fit-tested half mask respirator with P3 or ABEK filters. - Admin: Rotate personnel, limit exposure duration. | 5 | 2 | 10
8 | 3C. EXECUTION OF WELDING (TIG WELDING/GRINDING IN CONFINED SPACE) Fire/Explosion from Hot Work (welding/grinding sparks, combustibles) | Severe burns, fire spread, damage to vessel or environmental pollution | 5 | 4 | 20 | - Engineering: Remove/cover combustible materials within 10m working radius. - Engineering: Fire blanket deployed below/around work area. - Admin: Fire watch with extinguisher at entry/inside space. - Admin: Regular monitoring for flammable vapor with PID/multi-gas detector. - Admin: Full hot work permit in place. - PPE: Flame-retardant coveralls, gloves, eye and face protection. | 5 | 2 | 10
9 | 3C. EXECUTION OF WELDING (TIG WELDING/GRINDING IN CONFINED SPACE) High Noise from grinder (>85dB) | Hearing loss, distraction leading to incident | 4 | 3 | 12 | - Engineering: Use dampening barriers if possible. - Substitution: Use low-noise tools if available. - PPE: Mandatory use of hearing protection (ear plugs or muffs EN352 certified). | 4 | 1 | 4
10 | 3C. EXECUTION OF WELDING (TIG WELDING/GRINDING IN CONFINED SPACE) Eye injury from arc flash or flying particles (welding, grinding) | Temporary/permanent vision loss, lacerations | 4 | 3 | 12 | - Engineering: Use of welding screens, segregation of workspace. - PPE: Auto-darkening welding helmet, safety goggles/face shield, grinding visor. - Admin: All non-involved personnel excluded from area. | 4 | 1 | 4
11 | 3C. EXECUTION OF WELDING (TIG WELDING/GRINDING IN CONFINED SPACE) Burns from hot metal or welding torch | First/second degree burns, tissue damage | 4 | 3 | 12 | - Engineering: Use insulated clamps and shielded torches. - PPE: Flame-retardant gloves, long sleeves, apron. - Admin: Tools and hot metal marked 'HOT'. | 4 | 1 | 4
12 | 3C. EXECUTION OF WELDING (TIG WELDING/GRINDING IN CONFINED SPACE) Marine: Man Overboard during approaches to open deck in heavy rain | Drowning, hypothermia | 5 | 2 | 10 | - Engineering: Install guardrails or temporary barriers near open edges. - Admin: Work in pairs, radio check before deck exit. - PPE: Lifejacket when working at or near open deck edge as per vessel procedure. | 5 | 1 | 5
13 | 3C. EXECUTION OF WELDING (TIG WELDING/GRINDING IN CONFINED SPACE) Weather: Reduced visibility and increased slips due to heavy rain | Head or limb injury, possible falls | 4 | 3 | 12 | - Engineering: Adequate portable/explosion-proof lighting inside space. - Admin: Pause work if visibility drops below safe threshold. - PPE: Non-slip boots. | 4 | 1 | 4
14 | 4. DEMOBILIZATION / HOUSEKEEPING / FIRE WATCH Smoldering materials, re-ignition after hot work | Delayed fire, vessel damage | 5 | 3 | 15 | - Admin: Minimum 60-minute fire watch after hot works. - Engineering: Use thermal camera to inspect for hidden hot spots. - Admin: Remove all combustible waste and tools. | 5 | 1 | 5
15 | 4. DEMOBILIZATION / HOUSEKEEPING / FIRE WATCH Equipment left in dangerous condition (live cables, sharp tools, gas bottles) | Electric shock, trip hazard, unplanned ignition | 4 | 3 | 12 | - Admin: Full equipment check-out before leaving site. - Engineering: Disconnect and isolate power, bleed down any pressurized hoses. - PPE: Use gloves during cleanup. | 4 | 1 | 4

## Sheet1 (hidden)
Consequence/probability
1
2
3
4
5